## Sample Roadmap
ROADMAP - 2020
Q1 |  | Q2 |  | Q3 |  | Q4
Platform - Web / Mobile
© Copyright. upGrad Education Pvt. Ltd. All rights reserved
EPIC / FEATURE |  |  | EPIC / FEATURE |  |  |  | Disclaimer:
All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
|  | EPIC / FEATURE |  |  | EPIC / FEATURE |  | You can download this document from the website for self-use only.
Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
[6 empty] | EPIC / FEATURE | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
| Placeholder for Epics / Features added above, Add more details / edit the roadmap as required | [5 empty] | No material in this document will be modified, adapted or altered in any way.
No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
Any rights not expressly granted in these terms are reserved.

## PRODUCT ROADMAP
PRODUCT ROADMAP for HungerWoo !
QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4
JANUARY
FEBUARY
MARCH
APRIL
MAY
JUNE
JULY
AUGUST
SEPTEMBER
OCTOBER
NOVEMBER
DECEMBER
Home/Start Page
Restaurant Listing Page
Search Page
Menu Page
Order Page
Final Cart View
Scheduling Pre Order Page
Customise Pre Order
Offer Page
Order Tracking
Preferences
Subscription Page
Payment Gateway Page
Profile Page
Pay Later Option
Reminder for Food
App improvement
Bug Fixes

## PRODUCT BACKLOG
PRODUCT BACKLOG
S.No | Work Item Type | Work Item Title | Priority (P1, P2 etc) | Comments | Other details, if any
1 | Functionality | Landing page | 1 | MVP
2 | Functionality | Home/Start page | 1 | MVP
3 | Functionality | Restaurant Listing Page | 1 | MVP |  | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
4 | Functionality | Profile Page | 1 | MVP
5 | Functionality | Search Page | 1 | MVP |  | Disclaimer:
6 | Functionality | Menu Page | 1 | MVP |  | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
7 | Functionality | Order Page | 1 | MVP |  | You can download this document from the website for self-use only.
8 | Functionality | Final Cart View | 1 | MVP |  | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
9 | Functionality | Offer and discount page | 1 | MVP |  | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
10 | Functionality | Scheduling Pre order Page | 1 | MVP |  | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
11 | Feature | Customise Pre Order | 1 | MVP |  | No material in this document will be modified, adapted or altered in any way.
12 | Functionality | Filter and Search Option | 1 | Search |  | No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
13 | Functionality | Payment Gateway Page | 2 | MVP |  | Any rights not expressly granted in these terms are reserved.
14 | Feature | Mobile Logging OTP | 2 | Log In
15 | Feature | Order tracking page | 2 | Order Tracking
16 | Bug Fixes | Bug Fixes | 2 | Enhancement
17 | Feature | Preferences | 2 | Product page
18 | Functionality | Customer Support Page | 2 | Product page
19 | Functionality | Rating and review Page | 2 | Feedback
20 | Feature | Subscription page | 3 | Subscription
21 | Feature | Pay later option | 3 | Payment
22 | Feature | Reminder for Food | 3 | Enhancement
23 | App Improvement | App improvement | 3 | Enhancement

## SPRINT BACKLOG
SPRINT BACKLOG - Sprint 1
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature | Priority | Status | Comments | Other details, if any
1 | Feature | As a new user , the user shall be able to create an account on the app by entering a unique user name and password | Profile Creation | P1 | To Do
2 | Feature | As a new user , the user shall be able to create an account through phone number an OTP | Profile Creation | P1 | To Do |  |  | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
3 | Feature | As a new user , the user shall be able to link Facebook account to create | Profile Creation | P2 | To Do
4 | Feature | As a new user , the user shall be able to link Gmail account to create | Profile Creation | P2 | To Do |  |  | Disclaimer:
5 | Feature | As an existing user, I shall be able to enter credentials and log in. | Profile Creation | P1 | To Do
6 | Feature | As an exisitng user, I can click reset password button to receive link to reset my password on email | Profile Creation | P1 | To Do |  |  | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
7 | Feature | As an exisitng user , I shall be able to view and edit my profile. | Profile Creation | P1 | To Do
8 | Feature | Upon logging in with the user credentials, I shall be able to logout. | Profile Creation | P1 | To Do |  |  | You can download this document from the website for self-use only.
9 | Feature | As an exisitng user , I shall be able to set preferences and save. | Set Preferences | P2 | To Do
10 | Feature | As a guest/user, a home page shall be displayed with top-rated dish suggestions and popular restaurants/chefs serving near me. | Home Page | P1 | To Do
11 | Feature | As a registered user, a home page shall be displayed with top-rated dish suggestions and popular restaurants/chefs based on my preferences. | Home Page | P1 | To Do
12 | Feature | As a guest/ user, a home page shall be display infromation about company,Help, customer service,cities served etc. | Home Page | P1 | To Do
SPRINT BACKLOG - Sprint 2 | [7 empty] | Any rights not expressly granted in these terms are reserved.
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature | Priority | Status | Comments | Other details, if any
1 | Feature | As a user, I shall be allowed the manully set the location. | Profile Creation | P1 | To Do |  |  | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
2 | Feature | As a user, the app shall auto-detect my location and populate the location and allow the user to override the set location. | Profile Creation | P2 | To Do |  |  | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
3 | Feature | As a user, I shall be able to enter free text in the search box and click on search. | Search | P2 | To Do |  |  | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
4 | Feature | As a user, upon entering the search text, a list shall be displayed with a list of results comprising of matching restaurant name, dish name or chef name. | Search | P2 | To Do |  |  | No material in this document will be modified, adapted or altered in any way.
5 | Feature | As a user, upon entering the search text, a list results shall show the relevant pic along with additional details such as rating, type of cuisine or delivery mode. | Search | P1 | To Do
6 | Feature | As a user, I shall be able to sort the list results with various options such as price, popularity,rating and ETA. | Search | P1 | To Do
7 | Feature | As user when I scroll the search results, next 10 results are automatically shown | Search | P2 | To Do
8 | Feature | As a user, I shall be able to filter the search results based on price, popularity, rating, cuisine etc. | Filter | P1 | To Do
9 | Feature | As a user, upon clicking in a Dish icon, the page shall display overview, additional photos,reviews etc in a seperate layout | View and Place Order | P2 | To Do
10 | Feature | As a user, upon clicking on a Restaurant menu/chef menu, I shall be able to see dishes served, recommendations etc. | View and Place Order | P2 | To Do
11 | Feature | As a user, upon clicking Add to Cart button, I shall be able to add dishes to my cart. | View and Place Order | P1 | To Do
12 | Feature | As a user, upon clicking on quantity dropdown in Shopping Cart Page, I shall be able to change the quantity of the food item | View and Place Order | P1 | To Do
13 | Feature | As a user, I shall be able to delete items from the cart | View and Place Order | P1 | To Do